## Build Order
ZOAURO Super Admin + Zonal Admin: modules and build order
Progress updated 2026-10-15 from the code on main (local and GitHub). Progress % = share of the Phase 1 scope built and tested (API + screens + tests). Rows from 17 on were added from the roadmap v2 and the owner decisions of 2026-10-14.
Order | Module ID | Module | Built by | Why it sits here | Status | Notes | Progress | Current focus
0 | FND | Platform foundation (monorepo, database + migrations, API core, app shell, ZOAURO theme, grouped menu with Soon pages) | Dev 3 | Everything else runs on it. | Done | On main and pushed. 7+ migrations applied to zoauro; shell, theme, page finder, toasts; every unbuilt module has a plan page. Production build starts (pnpm --filter @zoauro/api smoke:start: /api/health and /api/ready 200). | 100%
1 | M01 | Auth and Sessions (login tabs, 2FA, lockout, password reset) | Dev 2 | Every other screen and API call needs a logged-in user. | Done | Built on main: password, CSRF, sessions (cap 3, remember me), 2-step picker (first sign-in by email code, authenticator added in Account security, SMS), backup codes, step-up re-auth, recovery CLI, sign-in screens in the theme, e2e 14/14 green; manual test procedure in doc 58. Left: SMS goes live once the MSG91 DLT template is registered; admin email update waits for the owner approval. | 95% | Email update (approval)
2 | M04 | Audit and Logs | Dev 3 | Every write in every later module must be audited; cheaper to build before them than to retrofit. | In review | System Logs (activity + sign-ins), zone Activity tab, Recent Activities, DENIED rows. Left: integration events link (needs M21), retention jobs. | 90%
3 | M02 | Zones | Dev 1 | Vendors, partners, orders and team members all belong to a zone, so zones must exist first. | In review | API + screens done (list, form with pincode overlap check, detail, activate/deactivate, pincodes, resolver), e2e green. Per-zone service switches added (D92); migration applied to zoauro on 2026-10-15. Left: zone Suspend (decision Q2, doc 59), zone setting overrides. Later: CSV pincode import. | 90% | Suspend (decision Q2)
4 | M03 | Zonal Admins and Access Control (accounts, Zone Teams, Access Profiles, Member Access editor, Preview, History) | Dev 3 | Rule engine for who can see and do what in each zone; every later module checks it. | Done | API (24 integration tests) and all screens: accounts, member access editor with grant/deny and refund limits, preview, profiles matrix, zone teams, history. e2e green. | 95%
5 | M05 | Zone Scope Switcher |  | Depends on the access rules from step 4; small, but every Zonal Admin screen uses it. | Not started | A read-only "my zones" chip exists in the top bar. Switcher designed in doc 59 (Phase 4 of the Control & Governance spec). | 10%
6 | M06 + M07 | Restaurants and Homemakers | Dev 1 | Orders need a vendor to point at; first modules to use zone and permission rules in the UI. | In progress | Being built by the colleague on branch feature/m06-m07-restaurants-homemakers (its own foundation). To be moved onto main when the colleague says it is finished; the tables already exist on main. | 30% | Colleague (Dev 1)
7 | M08 | Menu / Food Items |  | Needs vendors to exist; an order needs items. | Not started | Tables exist on main. Item changes go through approval (R09). | 0%
8 | M11 | Orders (state machine, intake API, simulator, list, detail) | Dev 2 | Core of the product and the longest chain, so it starts early. The simulator lets others test without a customer app. | In progress | Colleague branch dev_cb has an order service (state transitions, no database yet). To be moved onto main when finished; tables exist on main. Order number format configurable (D88). | 15% | Colleague (Dev 2)
9 | M09 + M10 | Customers and Delivery Partners |  | Order assignment needs partners; order history needs customers. Built in parallel with orders. | Not started | Partner onboarding requests with document checklist (R12, D97). | 0%
10 | M17 | Real-time and Notifications |  | Live alerts need orders; per-zone and per-permission event filtering must be correct before launch. | Not started | Notifications grantable to Zonal Admins (D94); promotions need Super Admin approval; in-app + email first (D99); timing configurable (D100). | 5%
11 | M12 | Payments (gateway, signed webhooks, ledger) |  | Money logic needs finished orders; needs gateway decision D6 by about week 10. | Not started | Gateway decided: Razorpay (D6). COD and wallet kept separate. | 0%
12 | M13 + M14 | Refunds and COD Settlement |  | Refunds need payments and per-member limits; COD needs delivered orders and partner cash balances. | Not started | Refund limits per zone (D13), two approvers above Rs 10,000 (D95), rules configurable (D96), refund letters (R16). | 0%
13 | M15 | Payouts and Reconciliation |  | Needs payments and refunds settled; not needed to run live operations. | Not started |  | 0%
14 | M16 | Dashboards | Dev 3 | Totals only make sense once orders and money exist; tiles hide without permission. | In progress | Super Admin and Zonal dashboards live with real data (zones, security, recent activity, my zones and limits). Order and money tiles come with those modules. | 40%
15 | M18 | Global Search |  | Searches orders, vendors, customers, so they must exist; results must respect permissions. | Not started | A page finder (Ctrl+K) is live in the top bar. | 5%
16 | M19 | Settings and Security | Dev 3 | Only needs login, so it fills schedule gaps; 2FA and session rules done before hardening. | In progress | Security settings live (2-step policy, status, SMS resume). Platform settings are the "Dynamic settings" row below. | 50%
After pilot | M20 | Extras (Analytics, Offers & Loyalty, Reviews) |  | In Figma but not part of the launch goal. | Not started | Support moved to Phase 1 (row "Support desk"). Loyalty values all configurable, no defaults (D101). | 0%
17 | CP | Super Admin Control Panel and per-zone services (Restaurants, Home Food, Hotel Booking switches) | Dev 3 | Owner: every service and control is allocated by the Super Admin (D92). | Done | API + screens done (zones x services switches, Services tab per zone, one place for every control); e2e green; migration applied to zoauro 2026-10-15 and verified. Blocking new onboarding and orders in a switched-off zone arrives with those modules. | 100%
18 | SET | Dynamic platform settings (refund limits per zone, two-approver amount, refund rules, onboarding documents, support SLAs, notification timing, order-number format, SMS provider, loyalty values) | Dev 3 | Owner: values decided by the Super Admin, not hard-coded (D13, D68, D88, D95-D101). | In progress | Owner spec "Control & Governance" (2026-10-15). Phase 0 plan in doc 59: default applies until the Super Admin saves a value; zone overrides; settings history. Waiting for the owner to approve the plan and decisions Q1-Q8. | 15% | Phase 0 plan (approval)
19 | R01 | Restaurant Onboarding requests (queue, review, approve / reject / more info) |  | Restaurants join through a reviewed request (roadmap R01, R02). | Not started | Plan page in the menu. Needs M06 + documents checklist (D97). | 0%
20 | R09 | Food Item change requests (add, edit, price, availability, remove) |  | Menus change only through approval (roadmap R07-R09). | Not started | Plan page in the menu. Needs M08. | 0%
21 | R12 | Delivery Partner onboarding requests |  | Partners join through verification (roadmap R12). | Not started | Plan page in the menu. Needs M10 + documents checklist (D97). | 0%
22 | R13 | Zonal Admin access requests |  | Zonal Admins ask, Super Admin decides; no self-approval (roadmap R13). | Not started | Plan page in the menu. Builds on M03. Designed in doc 59 (Phase 4 of the Control & Governance spec). | 0%
23 | R10 + R11 | Zone and Admin performance |  | Zone results and admin performance, not revenue alone (roadmap R10, R11). | Not started | Needs orders and payments. | 0%
24 | SUP | Support desk (zone queues, SLAs, assignment, refund-linked tickets) |  | Moved to Phase 1 by the owner (D93, D98). | Not started | Grantable to Zonal Admins (view, edit). SLA defaults: reply 2 h, resolve 24 h, escalate 12 h, reopen 7 days. | 0%
25 | HOTEL | Hotel Room Booking |  | New module requested by the owner, Phase 1 (D91). | Not started | Scope to be designed; off by default in every zone (D92). | 0%
Summary
Rows done
Rows in review (built, waiting for an approval or a small follow-up)
Rows in progress
Rows not started
Rows total
Overall progress (every row counts the same)
Core modules first: foundation, M01, M04, M02, M03 (rows 0-4)
|  | Working on now | Control & Governance module: Phase 0 plan (doc 59) waits for the owner approval; then settings, access requests (R13) and the zone switcher (M05). Admin email update waits for the owner "approved". After that: Delivery Partners. Restaurants/Homemakers and Orders with the colleagues.
|  | Dev 1 | Chittra priya
|  | Dev 2 | Maharaj
|  | Dev 3 | Lakshminarasimma